## Sheet1
Website	All pages	Localized branding	IE Proudly Made in Ireland	Change to "Proud to be Irish"	Add Guaranteed Irish logo & click-through to Blessington assembly blog	High	Open	Dev
Website	HERO	CTA text contrast	CTA 'Configure your TIM' is white in light mode	Switch CTA to black in light mode		Medium	Open	Frontend
Website	HERO	Call-to-action for waitlist	Pre-orders Jan 2026		Add 'Join waitlist' below <btn> (mailing list exists)	Medium	Open	Frontend
Website	HERO	Repetitive value props	'Premium Quality' & 'Irish Craftsmanship' too similar	Rewrite 'Premium Quality' to emphasize software design		Low	Open	Content
Website	Pricing	Incorrect TIM Max price	TIM Max at 1299		Change to 1499; highlight Developer Mode (not 'jailbreak')	High	Open	Product
Store	Products	Product images	No images/colors for Pro	Upload clear images	Add color choices for Pro	Medium	Open	Designer
Store	Upgrades	Upgrade options for Tiny TIM	Still shown	Remove upgrade options	Add 'Upgrade to Just TIM' banner	Medium	Open	Frontend
Configure	Tiny Tim	Upgrade CTA placement	Immediate highlight is pushy	Move upgrade below config	Show software greyed out after; new CTA with 10% discount	Medium	Open	UX
Configure	Tiny Tim	Free engraving	Free on all	Make €20 upgrade (not on Tiny, free on Max)	10 chars only, confirm, preview engraving	Low	Open	UX
Configure	Tiny Tim	Review summary	Address above config summary	Move summary to top		Low	Open	UX
Configure	Just Tim	Config step load	Loads bottom of page	Should load at top	Box selection: click anywhere	Medium	Open	UX
Configure	Just Tim	Software add-ons savings	'Save 100/50'	Add '*vs buying later in app'		Low	Open	Content
Configure	Tim Pro	'Jailbreak' Access	'Jailbreak' Access	Rename 'Enable Developer Mode'		Medium	Open	Content
Configure	Tim Pro	Software add-ons persistence	Selected add-ons applied to new config	Clear cache on step 1/cart confirm		Medium	Open	Dev
Website	About	Location	Made in Ireland IE	Change to 'Guaranteed Irish'		Low	Open	Content
Website	About	Resource Efficient	Resource Efficient		'From EUR per day'	Low	Open	Content
Website	About	Community Driven	Community Driven		For Pro, enable user feedback/challenge	Low	Open	Product
Website	About	Location reference	'Made in Ireland'...Dublin	Change to 'Wicklow'	Add 'Garden of Ireland'	Low	Open	Content
Website	About	Journey section	Our Journey		Add founder frustration with digital subs/smart tech	Low	Open	Content
Website	Support	Software update policy	Unlimited software updates		'Lifetime software updates* until version deprecated'	Medium	Open	Content
Website	Support	Phone support	'Premium Customers'	Change to 'Pro Customers Log In Required' (show inside app only)		Medium	Open	Frontend
Website	Enhancements	Product Roadmap			Roadmap: upcoming apps/hardware/limited editions	Low	Open	Content
App	Auth	Brand/identity	'Set up your local TIM server'	Change to 'Set up your local This Is Mine server'	Allow login/setup first	High	Open	Mobile
App	Onboarding	Founder message	Not shown	Add at beginning		Medium	Open	UX
App	Onboarding	Storage savings	Generic savings after purchase	Remove generic ref	Personalize by model (256/512/etc.)	Medium	Open	UX
App	Onboarding	Setup skipping	'Skip' button doesn't work	Fix nav or remove		Medium	Open	Mobile
App	Onboarding	Folder scan UX	Only does savings calc	Focus on folder mirroring and mapping	Prompt mapping for unmatched folders	Medium	Open	Mobile
App	Onboarding	Setup location	Not web-based	Migrate onboarding to web on user’s device	Announce headless/QR/packaging flow	High	Open	Dev
App		Connection speed UI	'Testing' not functional	Change CTA to 'Test Connection'	Amber/red for latency	Low	Open	Mobile
Files		Search bar	Only searches current folder	Enable global directory search	Add file type/size/date filters	High	Open	Backend
App		Device name	Always shows 'T.I.M Server'	Show custom name from onboarding		Low	Open	Backend